## Table 1
www.setupmyhotel.com Hotel Pre-Opening Template (
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
| Hotel Go Live Date | 2013-12-01
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
1 | Administration & General
2 | Controls
3 | Insurance
4 | Determine Insurance Needs
5 | Research Insurance Providers
6 | Select Insurance Providor(s)
7 | Ensure insurance is activated
8 | Purchasing & Receiving
9 | Implement purchase order system
10 | Develop Inventory Management Reports
11 | Payroll
12 | Establish payroll procedures
13 | SOP's
14 | Develop A&G SOP's
15 | Accounting Manual
16 | Establish hotel credit policy and procedures
17 | Develop internal forms
18 | Set-up Cash Deposit Procedures
19 | Banking
20 | Set-up bank accounts
21 | Set-up credit card agreements
22 | Obtain licenses and permits
23 | Liquor License
24 | Business Licenses
25 | Environmental Permits
26 | Sales Tax Permit
27 | Third Party Agreements
28 | Leases
29 | Retail
30 | Develop Standards of Performance
31 | Develop RFP
32 | Release RFP
33 | RFP Deadline
34 | Lesee Selected
35 | Lease executed
36 | Employee Orientation
37 | F&B
38 | Develop Standards of Performance
39 | Develop RFP
40 | Release RFP
41 | RFP Deadline

## Table 2
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
42 | Lesee Selected
43 | Lease executed
44 | Employee Orientation
45 | Financial Reporting
46 | Daily Revenue Report
47 | Daily Labor Report
48 | Period Financial Statements
49 | Period Ending Management Report
50 | Planning
51 | Proforma
52 | Annual Strategic Plan
53 | Complete First Year Operating Budget
54 | Complete Pre-opening Budget
55 | Develop forecasting program
56 | 3 Day Forecast (Rooms)
57 | 10 Day Forecast (Rooms and F&B)
58 | Weekly Forecast (Total Property)
59 | IT
60 | Manual Back Up - SOP's
61 | Timekeeping System
62 | Telephone System
63 | Simplex
64 | Payroll System
65 | OCV
66 | Back Office System
67 | Sales/Catering System
68 | PMS
69 | POS
70 | Systems
71 | PMS
72 | Develop RFP
73 | Develop Business Process
74 | Determine Workstations: Amount and Location
75 | Determine Budget
76 | Release RFP
77 | RFP Deadline
78 | System Selected
79 | System Specifications Determined
80 | System Installed & Tested
81 | System Training
82 | POS
83 | Develop Business Process
84 | Determine Workstations: Amount and Location
85 | Determine Budget
86 | Release RFP
87 | RFP Deadline
88 | System Selected
89 | System Specifications Determined
90 | System Installed & Tested
91 | System Training

## Table 3
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
92 | Develop RFP
93 | Develop Business Process
94 | Determine Workstations: Amount and Location
95 | Determine Budget
96 | Release RFP
97 | RFP Deadline
98 | System Selected
99 | System Specifications Determined
100 | System Installed & Tested
101 | System Training
102 | Keylock System
103 | Develop RFP
104 | Develop Business Process
105 | Determine Workstations: Amount and Location
106 | Determine Budget
107 | Release RFP
108 | RFP Deadline
109 | System Selected
110 | System Specifications Determined
111 | System Installed & Tested
112 | System Training
113 | Back-Office System
114 | Develop RFP
115 | Develop Business Process
116 | Determine Workstations: Amount and Location
117 | Determine Budget
118 | Release RFP
119 | RFP Deadline
120 | System Selected
121 | System Specifications Determined
122 | System Installed & Tested
123 | System Training
124 | Entertainment System
125 | Television
126 | Develop RFP
127 | Develop Business Process
128 | Determine Workstations: Amount and Location
129 | Determine Budget
130 | Release RFP
131 | RFP Deadline
132 | System Selected

## Table 4
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
133 | System Specifications Determined
134 | System Installed & Tested
135 | System Training
136 | Music
137 | Develop RFP
138 | Develop Business Process
139 | Determine Workstations: Amount and Location
140 | Determine Budget
141 | Release RFP
142 | RFP Deadline
143 | System Selected
144 | System Specifications Determined
145 | System Installed & Tested
146 | System Training
147 | Timekeeping System
148 | Develop RFP
149 | Develop Business Process
150 | Determine Workstations: Amount and Location
151 | Determine Budget
152 | Release RFP
153 | RFP Deadline
154 | System Selected
155 | System Specifications Determined
156 | System Installed & Tested
157 | System Training
158 | Telephone System
159 | Develop RFP
160 | Develop Business Process
161 | Determine Workstations: Amount and Location
162 | Determine Budget
163 | Release RFP
164 | RFP Deadline
165 | System Selected
166 | System Specifications Determined
167 | System Installed & Tested
168 | System Training
169 | Connectivity (Guest & Admin)
170 | Develop RFP
171 | Develop Business Process
172 | Determine Workstations: Amount and Location
173 | Determine Budget

## Table 5
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
174 | Release RFP
175 | RFP Deadline
176 | System Selected
177 | System Specifications Determined
178 | System Installed & Tested
179 | System Training
180 | Group/Catering Sales Management System
181 | Develop RFP
182 | Develop Business Process
183 | Determine Workstations: Amount and Location
184 | Determine Budget
185 | Release RFP
186 | RFP Deadline
187 | System Selected
188 | System Specifications Determined
189 | System Installed & Tested
190 | System Training
191 | Secondary System
192 | Develop RFP
193 | Develop Business Process
194 | Determine Workstations: Amount and Location
195 | Determine Budget
196 | Release RFP
197 | RFP Deadline
198 | System Selected
199 | System Specifications Determined
200 | System Installed & Tested
201 | System Training
202 | Develop comment card/guest feedback program
203 | Determine survey sources/review samples
204 | Develop comment forms
205 | Develop survey procedures/system
206 | Print comment cards/forms
207 | Printed Materials
208 | Business Cards
209 | Payroll Checks
210 | AP checks
211 | Purchase Requisitions/Orders
212 | Human Resources
213 | Staffing
214 | Organization

## Table 6
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
215 | Develop Organizational Chart
216 | Develop Staffing Guide
217 | Develop Hiring Schedule
218 | Customize Position "Must" Lists
219 | Customize Position Job Descriptions
220 | Develop Incentive Plans
221 | Leadership Team
222 | Sales Managers/Reservation Sales Agents
223 | Managers
224 | Employees
225 | Develop reward/recognition programs for hourly employees
226 | Recruitment
227 | Management
228 | Hire Senior Management Team
229 | Select Search Firm(s)
230 | General Manager
231 | Director of Operations
232 | Director of Rooms
233 | Director of F&B
234 | Spa Director
235 | Hotel Controller
236 | Chief Engineer
237 | Revenue Manager
238 | Director of Human Resources
239 | Director of Sales & Marketing
240 | Hire Department Heads
241 | Select Search Firm(s)
242 | Purchasing Manager
243 | Front Office Manager
244 | Executive Housekeeper
245 | Food & Beverge Operations Manager
246 | Banquet Manager
247 | Beverage Manager
248 | Executive Chef
249 | Spa Manager
250 | Accounting Manager
251 | Hire Junior Managers
252 | Rooms
253 | Assistant Front Office Manager
254 | Guest Service Manager
255 | Chef Concierge

## Table 7
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
256 | Assistant Executive Housekeeper
257 | F&B
258 | Banquet Manager
259 | Restaurant Manager
260 | Dining Room Chef
261 | Banquet Chef
262 | Garde Manager
263 | Demi Chef
264 | Pastry Chef
265 | A&G
266 | Night Manager
267 | A&S
268 | Reservation Sales Manager
269 | Hire Sales Managers
270 | Director of Catering
271 | Senior Sales Manager
272 | Executive Meeting Manager
273 | Hire Catering Assistant
274 | Conference Service Manager
275 | Supervisors
276 | Rooms
277 | Front Office Supervisor
278 | Housekeeping/Floor Supv
279 | Housekeeping/Turndown
280 | Housekeeping/Night
281 | Bell Captain
282 | Chef Concierge
283 | Reservation Sales Coordinator
284 | Food & Beverage
285 | Dining Room Supervisor
286 | Maitre De
287 | Room Service Captain
288 | Banqet Captain
289 | Beverage Supervisor
290 | Cafeteria Supervisor
291 | Head Houseperson (Banquets)
292 | A&G
293 | Executive Administrative Assistant
294 | Accounting
295 | Credit Supervisor
296 | Lead Night Auditor

## Table 8
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
297 | Security
298 | Security Supervisor
299 | R&M
300 | Engineering Supv
301 | Engineering Administrative Assistant
302 | Spa
303 | Spa Supervisor
304 | Hourly
305 | Rooms
306 | Front Office
307 | Receptionist
308 | Telephone
309 | Bell Attendant
310 | Door Attendant
311 | Driver
312 | Valet Office Attendant
313 | Valet
314 | Concierge
315 | Night GSA/Night Auditor
316 | Housekeeping
317 | Room Attendant
318 | Housekeeping Clerk
319 | House Person
320 | Room Attendant
321 | Floor Care Attendant
322 | Public Area Attendant
323 | Turndown Attendant
324 | Night Cleaner
325 | Uniform Attendant
326 | Laundry
327 | Laundry Attendant
328 | F&B
329 | Casual Restaurant
330 | AM Host/Hostess
331 | AM Server
332 | AM DRA
333 | PM Host/Hostess
334 | PM Server
335 | PM DRA
336 | Fine Dining Restaurant
337 | Sommelier

## Table 9
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
338 | Waiter
339 | DRA
340 | Host/Hostess
341 | Back Waiter
342 | Afternoon/High Tea
343 | Runner
344 | Server
345 | Culinary
346 | Banquet Cook
347 | Prep Cook
348 | Pantry Cook
349 | Pastry Cook
350 | Demi Cook
351 | AM Cook
352 | PM Cook
353 | Banquet Cook
354 | Cafeteria Attendant
355 | Buffet Attendant
356 | Beverage
357 | Bartender
358 | Barback
359 | Cocktail Server
360 | Banquets
361 | Server
362 | Houseperson
363 | Temporary Staff
364 | In-Room Dining
365 | Server
366 | Coordinator
367 | Spa
368 | Receptionist
369 | Therapists
370 | R&M
371 | Engineer I
372 | Engineering II
373 | Engineering III
374 | HVAC
375 | Painter
376 | Preventative Maintenance Tech
377 | A&G
378 | Security

## Table 10
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
379 | Hours of Work
380 | Time Clocks/Time Keeping
381 | Solicitation
382 | Associate Liaisons
383 | Military Leave
384 | Worker's Compensation Leave
385 | FMLA Leave
386 | Personal Leave
387 | Email/Vmail
388 | School Leave
389 | Computer Equipment
390 | Confidentiality
391 | Reward & Recognition Program
392 | Incorporate Parent Company SOP's
393 | Develop MDSD Books/Procedures
394 | Develop Internal HR Related Forms
395 | Training
396 | Service
397 | Develop Service Standard Philosophy
398 | Purchase Standards Manual
399 | Customize Standards Manual
400 | Develop Service Standards by Department/Position
401 | Develop Job Skill Training by Department
402 | Develop associate handbook
403 | Sales and Catering Training
404 | Develop Sales Training Program
405 | Conduct Sales Training Program
406 | Develop Catering Training Program
407 | Conduct Catering Training Program
408 | Management Training
409 | Company Orientation
410 | Interview/Recruitment Training
411 | Team Building/Building an Effective Team
412 | Train the Trainer (Skills and Knowledge Training)
413 | Human Resources Procedures
414 | BootCamp
415 | Manager's Role
416 | Active Listening/Effective Communication
417 | Communicating and Gaining Commitment to Standards
418 | Situational Leadership
419 | Effective Coaching

## Table 11
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
420 | SOP's
421 | Develop Spa SOP's
422 | Printed Materials
423 | Spa Menu
424 | Rooms
425 | SOP's
426 | Develop Rooms Division SOP's
427 | Printed Materials
428 | Privacy Please Signs
429 | Privacy Courtesy Note
430 | Umbrellas
431 | Telephone Pads
432 | Dialing Instructions
433 | Driving Directions
434 | VIP Note Cards/envelopes
435 | Fax Delivery Envelopes
436 | Guestroom Note Pad
437 | Valet Laundry Bag
438 | Valet Laundry Price Sheet
439 | Shoe Shine Bag
440 | Shoe Shine Instructions
441 | Activity Calendar
442 | Newsletter
443 | PBX
444 | PBX Cut-Over from Pre-opening Office
445 | Guest Services
446 | Develop VIP program
447 | Transportation
448 | Vehicle Acquisition
449 | Finalize schedules & routes
450 | Review samples/pricing
451 | Order final selection
452 | Receive final selection
453 | Apply logo
454 | Develop preventive maintenance program
455 | Vehicles in service
456 | Roadwork
457 | Determine route
458 | Evaluate road condition
459 | Make adjustment
460 | Housekeeping

## Table 12
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
461 | Contract Valet Dry Cleaning Service
462 | Establish quantities and specifications
463 | Compile a list of contractors
464 | Interview contractors
465 | Receive proposals
466 | Award contract
467 | Service available
468 | Uniform Processing
469 | Develop uniform issuance/storage procedures
470 | F&B
471 | SOP's
472 | Develop F&B Division SOP's
473 | Store Room
474 | Establish Room locations
475 | Develop Organization and Item Storage Locations
476 | Develop Requisition Procedures
477 | Employee Dining Room
478 | Develop Hours of Operation/Staggered Meal Periods
479 | Training of Staff
480 | Fire & Test All Equipment
481 | Area Cleaned
482 | Finalize 20 Day Rotational Menu
483 | Develop Pre Menu Planner
484 | Develop Order Guide
485 | Finalize Any Needed Purchases/Small Wares
486 | Outlet Menus
487 | Initial draft prepared
488 | Leadership Team Review
489 | Competitive Review/Analysis
490 | Notes to Chef
491 | New menus prepared
492 | Final Review
493 | Menu tasting
494 | Menu specs and costing prepared
495 | Menu Descriptions Available for Servers
496 | Dining Room - Table Tops
497 | Centerpiece - PM
498 | Finalize Specifications and Amount
499 | Review Samples
500 | Order Selection
501 | Selection Received

## Table 13
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
502 | Vase - AM
503 | Finalize Specifications and Amount
504 | Review Samples
505 | Order Selection
506 | Selection Received
507 | S&P Shakers
508 | Finalize Specifications and Amount
509 | Review Samples
510 | Order Selection
511 | Selection Received
512 | Sugar - AM
513 | Finalize Specifications and Amount
514 | Review Samples
515 | Order Selection
516 | Selection Received
517 | Sugar - PM
518 | Finalize Specifications and Amount
519 | Review Samples
520 | Order Selection
521 | Selection Received
522 | Room Service - Table Top
523 | Vase
524 | Finalize Specifications and Amount
525 | Review Samples
526 | Order Selection
527 | Selection Received
528 | S&P Shakers
529 | Finalize Specifications and Amount
530 | Review Samples
531 | Order Selection
532 | Selection Received
533 | Sugar
534 | Finalize Specifications and Amount
535 | Review Samples
536 | Order Selection
537 | Selection Received
538 | Banquets - Table Top
539 | Centerpieces
540 | Finalize Specifications and Amount
541 | Review Samples
542 | Order Selection

## Table 14
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
543 | Menu specs and costing prepared
544 | Menu Descriptions Available for Servers
545 | O,S&E
546 | ADA Equipment
547 | Finalize items & quantities
548 | Review samples/pricing
549 | Order final selection
550 | Receive final selection
551 | Stock
552 | Rooms Linen
553 | Develop bed linen & bath standard
554 | Review samples/pricing
555 | Order final selection
556 | Receive final selection
557 | Wash
558 | Make beds/stock baths
559 | China, Glass & Silver
560 | Finalize service standard & quantities
561 | Review samples/pricing
562 | Order final selection
563 | Receive final selection
564 | Wash
565 | Stock
566 | Glassware-Other
567 | Finalize service standard & quantities
568 | Review Samples/Pricing
569 | Order Final Selection
570 | Receive Final Selection
571 | Wash
572 | Stock
573 | F&B Linen
574 | Finalize service standard & quantities
575 | Review Samples/Pricing
576 | Order Final Selection
577 | Receive Final Selection
578 | Wash
579 | Stock
580 | Kitchen Smallwares
581 | Finalize service standard & quantities
582 | Review Samples/Pricing
583 | Order Final Selection

## Table 15
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
584 | Receive Final Selection
585 | Wash
586 | Stock
587 | Banquet Equipment
588 | Finalize service standard & quantities
589 | Review Samples/Pricing
590 | Order Final Selection
591 | Receive Final Selection
592 | Wash
593 | Stock
594 | Select and procure grand piano
595 | Guest Ice Machines
596 | Review samples/pricing
597 | Order final selection
598 | Receive final selection
599 | Install
600 | F&B Consumables
601 | Finalize items & quantities
602 | Review samples/pricing
603 | Order final selection
604 | Receive final selection
605 | Stock
606 | Guest Bath Amenities
607 | Finalize items & quantities
608 | Review samples/pricing
609 | Order final selection
610 | Receive final selection
611 | Stock
612 | Guestroom Amenities
613 | Finalize items & quantities
614 | Review samples/pricing
615 | Order final selection
616 | Receive final selection
617 | Stock
618 | Guestroom Hair Dryers
619 | Finalize items & quantities
620 | Review samples/pricing
621 | Order final selection
622 | Receive final selection
623 | Install
624 | Guestroom Cosmetic Mirrors

## Table 16
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
625 | Finalize items & quantities
626 | Review samples/pricing
627 | Order final selection
628 | Receive final selection
629 | Install
630 | Maintenance inventory
631 | Finalize items & quantities
632 | Review samples/pricing
633 | Order final selection
634 | Receive final selection
635 | Stock
636 | Maintenance Tools
637 | Finalize items & quantities
638 | Review samples/pricing
639 | Order final selection
640 | Receive final selection
641 | Stock
642 | Maintenance Equipment
643 | Finalize items & quantities
644 | Review samples/pricing
645 | Order final selection
646 | Receive final selection
647 | Stock
648 | Housekeeping Equipment
649 | Finalize items & quantities
650 | Review samples/pricing
651 | Order final selection
652 | Receive final selection
653 | Stock
654 | Housekeeping Guest Consumables
655 | Finalize items & quantities
656 | Review samples/pricing
657 | Order final selection
658 | Receive final selection
659 | Stock
660 | Housekeeping Cleaning Supplies
661 | Finalize items & quantities
662 | Review samples/pricing
663 | Order final selection
664 | Receive final selection
665 | Stock

## Table 17
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
666 | Spa Equipment
667 | Finalize items & quantities
668 | Review samples/pricing
669 | Order final selection
670 | Receive final selection
671 | Stock
672 | Spa Guest Consumables
673 | Finalize items & quantities
674 | Review samples/pricing
675 | Order final selection
676 | Receive final selection
677 | Stock
678 | Spa Cleaning Supplies
679 | Finalize items & quantities
680 | Review samples/pricing
681 | Order final selection
682 | Receive final selection
683 | Stock
684 | Rooms Print & Stationary (Registration, key packet, etc.)
685 | Guest Services Directory
686 | Review Samples
687 | Develop conent/mock-up
688 | Review proof
689 | Print final collateral
690 | Key Packet
691 | Review Samples
692 | Develop conent/mock-up
693 | Review proof
694 | Print final collateral
695 | Develop registration/check-out system and collateral
696 | Review Samples
697 | Develop conent/mock-up
698 | Review proof
699 | Print final collateral
700 | Administration/Sales Print & Stationary (paper system)
701 | Review Samples
702 | Develop conent/mock-up
703 | Review proof
704 | Print final collateral
705 | Uniforms
706 | Review samples

## Table 18
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
707 | Install
708 | Postage Machine
709 | Finalize items & quantities
710 | Review samples/pricing
711 | Order final selection
712 | Receive final selection
713 | Install
714 | Fax Machines
715 | Finalize items & quantities
716 | Review samples/pricing
717 | Order final selection
718 | Receive final selection
719 | Install
720 | Computers/Printers
721 | Finalize items & quantities
722 | Review samples/pricing
723 | Order final selection
724 | Receive final selection
725 | Install
726 | Pool Equipment
727 | Finalize items & quantities
728 | Review samples/pricing
729 | Order final selection
730 | Receive final selection
731 | Install
732 | Guestroom Safes
733 | Finalize items & quantities
734 | Review samples/pricing
735 | Order final selection
736 | Receive final selection
737 | Install
738 | Security
739 | Two-way radios
740 | Finalize items & quantities
741 | Review samples/pricing
742 | Order final selection
743 | Receive final selection
744 | Install
745 | Monitoring System
746 | Finalize items & quantities
747 | Review samples/pricing

## Table 19
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
745 | Order final selection
746 | Receive final selection
747 | Install
748 | Keys
749 | Finalize items & quantities
750 | Review samples/pricing
751 | Order final selection
752 | Receive final selection
753 | Stanchions
754 | Finalize items & quantities
755 | Review samples/pricing
756 | Order final selection
757 | Receive final selection
758 | Sales & Marketing
759 | Marketing Plan
760 | Purpose
761 | Story
762 | Design
763 | Care
764 | Authenticity
765 | Competition Analysis
766 | Pricing Analysis
767 | Spreading The Word
768 | Website/E-Commerce
769 | Publicity
770 | Promotions
771 | Sales Goals and Action Plans
772 | Revenue Management
773 | Implement group pace report
774 | Implement group evaluator model
775 | Establish stretch goals for Convention Services
776 | Establish group room contribution goals for Sales
777 | Develop daily transient demand by season
778 | Set SST's
779 | PMS Training
780 | Set restrictions in PMS
781 | Implement Rate Codes In PMS
782 | Enter Packages Into PMS
783 | Develop Merchandising Meeting agenda
784 | Develop daily/weekly/monthly reporting
785 | Develop forecasting system (daily, weekly, monthly, annual)

## Table 20
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
786 | Develop Selling Strategy Calendar
787 | Set Initial Selling Strategies
788 | Reservations
789 | Guest Letters
790 | Complete Basic Confirmation Letter
791 | Complete Current Package Confirmation Letters
792 | Create Insert with Cancellation/Change Policy
793 | Gift Certificates
794 | Develop Gift Certificate Options
795 | Develop SOP's
796 | On-Hold Message
797 | Complete On-Hold Message Recording
798 | Install On-Hold Message
799 | Pre-Opening Callers and Drop In's
800 | Phone Line Allocation
801 | Develop SOP's
802 | Develop Telephone Scripting
803 | Staff Training
804 | Training
805 | Select Third Party Sales Training Program
806 | Schedule Training
807 | Packaging
808 | Evaluate Valley Periods and Need Areas
809 | Develop Packages
810 | Develop Schedule For Package Roll Outs
811 | Names
812 | Conduct Area/Suite Naming Exercise
813 | Add to Fact Sheet
814 | Select AV provider
815 | Determine scope of work
816 | Compile list of bidders and interview
817 | Receive proposals
818 | Award contract
819 | Develop AV Services Brochure
820 | SOP'S/Office Organization
821 | Develop sales proposals & contracts
822 | Implement Account Coverage Program
823 | Contract shopping service for Sales Managers
824 | Develop repeat guest program
825 | Direct Sales (Pre-opening)
826 | Complete Catering blitz of CBD

## Table 21
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
827 | Complete Business Travel blitz of CBD
828 | Leisure individual
829 | Identify direct mail/e-mail databases for leisure markets
830 | Initiate direct mail/e-mail campaign
831 | Spreading The Word
832 | Image/Brand
833 | Conduct Image/Brand Exercise
834 | Develop Positioning Statement
835 | Develop Tag Lines
836 | Develop Logo(s)
837 | Develop Graphics Standards Manual
838 | Advertising
839 | Develop advertising/media plan by market segement
840 | Create advertising
841 | Media buys
842 | Establish Tracking Mechanism for advertising campaign
843 | Launch advertising campaign
844 | Establish listings in directories (HTI, OHG, OAG, Official meeting facilities guide)
845 | Develop in-room TV Promotion Video
846 | Establish local yellow pages line listing
847 | Evaluate potential of co-op advertising with CVB, etc.
848 | Affiliations
849 | Determine Need (Mobil, AAA, Preferred, LHW, etc.)
850 | Coordinate Inspections
851 | Establish Lodging Association Membership
852 | Establish Restaurant Association Membership
853 | Establish Chamber Membership
854 | Sales Collateral
855 | Develop facilities guide/presentation folder
856 | Develop Pre-Opening Brochure
857 | Develop Permanent Brochure
858 | Develop Spa Brochure
859 | Develop ancillary sales collateral/stationery
860 | Develop Press Kit
861 | Develop Property Maps
862 | Develop Key Card Design
863 | Develop Tariff Cards
864 | Photography/Video
865 | Coordinate photo shoot for permanent brochure
866 | Photo shoot
867 | Photography available

## Table 22
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
868 | Video Shoot
869 | Video Available
870 | Public Relations
871 | Hire PR Firm
872 | Develop Media Kit
873 | Write the Story
874 | Develop hotel fact sheet
875 | Develop Bio's
876 | Select Photography
877 | Solicit Editorials
878 | Develop Media Visit Schedule
879 | Develop community/regional partnerships (Arts, Film, etc.)
880 | Establish listing/contact with local organizations (Chamber, CVB, etc.)
881 | Soft-opening PR Activities
882 | Establish Pre-opening Date
883 | Gifts
884 | Select Client/VIP Gifts
885 | Procure Client/VIP Gifts
886 | Select Staff/Management Gifts
887 | Procure Staff/Management Gifts
888 | Construction Party
889 | Determine list of attendees
890 | Determine dates
891 | Develop invitation
892 | Develop invitation lists
893 | Mail invitations
894 | Detail events
895 | Develop Program
896 | Budget
897 | Staffing Needs
898 | Parking and Transportation
899 | Floral and Decorations
900 | Entertainment
901 | Photography
902 | F&B
903 | Develop Menus
904 | Procure Food
905 | Procure Beverage
906 | Develop Amenities
907 | Procure Rentals
908 | Pre-opening receptions

## Table 23
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
909 | Determine list of target groups
910 | Determine dates
911 | Develop invitation
912 | Develop invitation lists
913 | Mail invitations
914 | Detail events
915 | Develop Program
916 | Budget
917 | Staffing Needs
918 | Parking and Transportation
919 | Floral and Decorations
920 | Entertainment
921 | Photography
922 | F&B
923 | Develop Menus
924 | Procure Food
925 | Procure Beverage
926 | Develop Amenities
927 | Procure Rentals
928 | Media Breakfast/Party
929 | Determine list of target groups
930 | Determine date
931 | Develop invitation
932 | Develop invitation lists
933 | Mail invitations
934 | Detail events
935 | Develop Program
936 | Budget
937 | Staffing Needs
938 | Parking and Transportation
939 | Floral and Decorations
940 | Entertainment
941 | Photography
942 | F&B
943 | Develop Menus
944 | Procure Food
945 | Procure Beverage
946 | Develop Amenities
947 | Procure Rentals
948 | Trial Visits
949 | Management/Staff Overnights for Testing

## Table 24
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
950 | Friends & Family Overnights
951 | VIP Overnights
952 | Grand Opening
953 | Hotel Opening Date
954 | Determine list of target groups
955 | Determine date
956 | Develop invitation
957 | Develop invitation lists
958 | Mail invitations
959 | Detail events
960 | Develop Program
961 | Budget
962 | Staffing Needs
963 | Parking and Transportation
964 | Floral and Decorations
965 | Entertainment
966 | Develop Ancillary Activities for Guests
967 | Procure Off-site Lodging
968 | Photography
969 | F&B
970 | Develop Menus
971 | Procure Food
972 | Procure Beverage
973 | Develop Amenities
974 | Procure Rentals
975 | On-line Reservations
976 | Reservations Sales Agents Training
977 | Develop On-line reservation web page
978 | Load revenue management information (set selling strategies and restrictions)
979 | Develop PMS configuration documentation
980 | Website
981 | Research Web Hosting
982 | Select Web Host
983 | Design Web Pages
984 | Test & Feedback
985 | Load For Public Use
986 | Packages
987 | Leisure
988 | Determine need dates
989 | Determine target audience
990 | Develop package

## Table 25
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
991 | Develop package collateral/purchase advertising
992 | Launch package advertising
993 | Tour Group
994 | Determine need dates
995 | Determine target audience
996 | Develop package
997 | Develop package collateral/purchase advertising
998 | Launch package advertising
999 | Wedding
1000 | Determine need dates
1001 | Determine target audience
1002 | Develop package
1003 | Develop package collateral/purchase advertising
1004 | Launch package advertising
1005 | Repairs & Maintenance
1006 | Printed Materials
1007 | Maintenance Performed Courtesy Note
1008 | Cleaning Chemicals
1009 | Select warewashing and housekeeping chemical supplier
1010 | Install warewashing and housekeeping chemical equipment
1011 | Domestic Water
1012 | Determine water treatment for central plant
1013 | Preventive Maintenance Programs
1014 | Develop rooms preventive maintenance program
1015 | Develop public areas preventive maintenance program
1016 | Develop equipment preventive maintenance program
1017 | Develop chiller, KWH, gas and watertemp./pressure logs and meter logs
1018 | Safety
1019 | Ensure fire extinguishers are in place
1020 | Develop Safety Committee
1021 | Model Rooms
1022 | Coordinate move of model rooms
1023 | Repair Response System
1024 | Develop work order system
1025 | Research and Procure Work Order Software
1026 | Training
1027 | Guest Key Card System training
1028 | Television/Movies training
1029 | Mechanical/HVAC training
1030 | Guestroom PM program training
1031 | Public space PM program training

## Table 26
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
1032 | Building management system training
1033 | Signage
1034 | Select and procure interior signage
1035 | Select and procure exterior signage
1036 | Pre-opening offices
1037 | Locate and Prepare pre-opening offices
1038 | Relocate Pre-opening Offices to Hotel
1039 | Develop MOD manual
1040 | Develop risk management manual/evacuation plan
1041 | Obtain fire department approval of fire/evacuation plan
1042 | MSD Sheets
1043 | Compile MSD Sheets for all Chemicals
1044 | Construction/Building Preparation
1045 | Kitchen
1046 | Substantial completion
1047 | Punch
1048 | Submit punch list to Chef, Dir. F&B for comments
1049 | Punch list items corrected
1050 | Equipment commissioning complete
1051 | Area cleaned
1052 | Restaurant
1053 | Substantial completion
1054 | Punch
1055 | Submit punch list to Chef, Dir. F&B for comments
1056 | Punch list items corrected
1057 | Equipment commissioning complete
1058 | Area cleaned
1059 | Meeting Space
1060 | Substantial completion
1061 | Punch
1062 | Submit punch list to Chef, Dir. F&B for comments
1063 | Punch list items corrected
1064 | Equipment commissioning complete
1065 | Area cleaned
1066 | Lounge/Bar
1067 | Substantial completion
1068 | Punch
1069 | Submit punch list to Chef, Dir. F&B for comments
1070 | Punch list items corrected
1071 | Equipment commissioning complete
1072 | Area cleaned

## Table 27
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
1073 | Retail
1074 | Substantial completion
1075 | Punch
1076 | Punch list items corrected
1077 | Area cleaned
1078 | Lobby
1079 | Substantial completion
1080 | Punch
1081 | Punch list items corrected
1082 | Area cleaned
1083 | Guestroom Punch
1084 | 7th Floor
1085 | Substantial completion
1086 | Punch
1087 | Punch list items corrected
1088 | Area cleaned
1089 | 6th Floor
1090 | Substantial completion
1091 | Punch
1092 | Punch list items corrected
1093 | Area cleaned
1094 | 5th Floor
1095 | Substantial completion
1096 | Punch
1097 | Punch list items corrected
1098 | Area cleaned
1099 | 4th Floor
1100 | Substantial completion
1101 | Punch
1102 | Punch list items corrected
1103 | Area cleaned
1104 | 3rd Floor
1105 | Substantial completion
1106 | Punch
1107 | Punch list items corrected
1108 | Area cleaned
1109 | 2nd Floor
1110 | Substantial completion
1111 | Punch
1112 | Punch list items corrected
1113 | Area cleaned

## Table 28
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
1114 | 1st Floor
1115 | Substantial completion
1116 | Punch
1117 | Punch list items corrected
1118 | Area cleaned
1119 | Spa
1120 | Substantial completion
1121 | Punch
1122 | Punch list items corrected
1123 | Area cleaned
1124 | Building Exterior
1125 | Substantial completion
1126 | Punch
1127 | Punch list items corrected
1128 | Area cleaned
1129 | Landscaping
1130 | Substantial completion
1131 | Punch
1132 | Punch list items corrected
1133 | Area cleaned
1134 | Back-Of-The-House
1135 | Substantial completion
1136 | Punch
1137 | Punch list items corrected
1138 | Area cleaned
1139 | Uniform Room
1140 | Substantial completion
1141 | Punch
1142 | Punch list items corrected
1143 | Area cleaned
1144 | Procure uniform racks
1145 | Install Uniform racks
1146 | Administrative/Front Office
1147 | Substantial completion
1148 | Punch
1149 | Punch list items corrected
1150 | Area cleaned
1151 | F,F&E Installation
1152 | Guestrooms
1153 | 7th floor
1154 | 6th floor

## Table 29
Note: You are not authorized to upload this format to any online / offiline medium without the permission of setupmyhotel.com ©
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
1155 | 5th floor
1156 | 4th floor
1157 | 3rd floor
1158 | 2nd floor
1159 | 1st Floor
1160 | Spa
1161 | Treatment Areas
1162 | Fitness Center
1163 | F&B
1164 | Lounge/Bar
1165 | Meeting Space
1166 | Restaurant
1167 | Public Areas
1168 | Lobby
1169 | Retail
1170 | Back-of-the-house
1171 | Administrative Offices
1172 | Kitchen/Engineering/Housekeeping
1173 | Testing/Documentation
1174 | All Areas Substantially Complete
1175 | Verify proper operation of all Life Safety equipment/systems
1176 | TCO
1177 | CO
1178 | Obtain "As Built" plans
1179 | Obtain all warranties and equipment information
1180 | Environmental/Recycling
1181 | Research Sources and Options
1182 | Develop SOP's
1183 | Contract Maintenance and Service Agreements
1184 | Rodent and Pest Control
1185 | Develop RFP
1186 | Receive Bids
1187 | Award Contract
1188 | Indoor Plants
1189 | Develop RFP
1190 | Receive Bids
1191 | Award Contract
1192 | Indoor Floral
1193 | Develop RFP
1194 | Receive Bids
1195 | Award Contract

## Table 30
www.mahotels.net
ID | Task Name | Duration in Days | Start Date | Proposed Finish | Actual Finish | Task Assigned to / Lead Staff | Remarks
1196 | Landscape
1197 | Develop RFP
1198 | Receive Bids
1199 | Award Contract
1200 | Snow Removal
1201 | Develop RFP
1202 | Receive Bids
1203 | Award Contract
1204 | Mechanical
1205 | Develop RFP
1206 | Receive Bids
1207 | Award Contract
1208 | Life Safety
1209 | Develop RFP
1210 | Receive Bids
1211 | Award Contract
1212 | Secure Background Music
1213 | Design Received
1214 | Design approved
1215 | Receive Bids
1216 | Contract awarded
1217 | Service installed and tested