## Administration and General
Hotel Live Date | 2018-10-10 |  | www.mahotels.net
ADMINISTRATION & GENERAL | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Insurance
Determine Insurance Needs | Pending | 30 | 2018-11-19 | 2018-12-19
Confirm Insurance Providers | Completed | 3 | 2018-11-12 | 2018-11-15
Ensure Insurance is activated | In Progress | 1 | 2018-10-10 | 2018-10-11
Purchasing & Receiving
Register with Hospitality Warehouse |  | 0
Identify Primary Suppliers |  | 0
Establish Credit with Suppliers |  | 0
Implement purchase order system |  | 0
Develop Inventory Management System |  | 0
Develop Requisition Procedures |  | 0
Leases
Confirm lease in place and copies available |  | 0
Printing and Stationery
Business Cards ordered |  | 0
Hotel Letterheads |  | 0
PMS Stationery |  | 0
GUEST Account Stationery |  | 0
Purchasing Order Forms |  | 0
Payroll & Personnel Forms |  | 0
Order Payroll Stationery |  | 0
Uniforms
Finalise Specifications and Quantities |  | 0
Order Uniforms |  | 0
Order STAFF Name Badges |  | 0
Transportation
Finalise Requirements |  | 0
Affiliations & Memberships
Establish Membership |  | 0
Community Policing Forums |  | 0
Pre-opening Offices
Locate and Prepare pre-opening offices |  | 0
Relocate Pre-opening Offices to Hotel |  | 0

## FINANCIAL PLAN
FINANCIAL PLAN | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Accounting Procedures
Obtain copy of Financial Plan Manual | Pending | 237 | 2018-01-07 | 2018-09-01
Order Accounting Package (ACCPAC) software |  | 0
Establish Hotel credit policy and procedures |  | 0
Set-up Accounts Procedures |  | 0
Obtain reporting formats |  | 0
Obtain Accounting Procedures Manuals |  | 0
Set-up Dictionary of Accounts |  | 0
Schedule training on ACCPAC |  | 0
Set-up Accounts STAFFING |  | 0
Recruit Key Accounts STAFF |  | 0
Payroll
Set-up salaries bank account |  | 0
Register to Bank Account |  | 0
Order Payroll software |  | 0
Order Payroll Stationery |  | 0
General Manager Checklist Completed post-opening |  | 0
Pre-opening Budget
Draft pre-opening budget |  | 0
Pre-opening budget approval |  | 0
Operating Forecasts completed |  | 0
Hotel Budgets
Draft 12 mth Operating Budget |  | 0
Draft Capex Budget |  | 0
Banking
Set-up Bank Accounts incl. Salary Account |  | 0
Arrange Overdraft Facilities |  | 0
Set-up credit card agreements |  | 0
Arrange Security Cash collection |  | 0
Determine Operating Cash requirements |  | 0
Asset Management
Open Fixed Asset Register |  | 0
Complete pre-opening asset stock takes |  | 0
See Admin & General |  | 0
See Risk Management |  | 0
See Legal Compliance |  | 0

## IT & SYSTEMS
IT & SYSTEMS | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Property Management System
Order placed | In Progress | 237 | 2018-01-07 | 2018-09-01
Service Level Agreement finalised |  | 0
Installation dates confirmed |  | 0
Data configuration set-up |  | 0
Data input and configuration |  | 0
Set restrictions in PMS |  | 0
Implement Rate Codes In PMS |  | 0
Enter Packages Into PMS |  | 0
System Installed & Tested |  | 0
Training dates confirmed |  | 0
Backup Systems & Protocol |  | 0
F&B Outlet POS Systems
Not Available |  | 0
0
Server & LAN Network
System specifications agreed |  | 0
Service Level Agreement finalised |  | 0
Equipment Orders placed |  | 0
Installation dates confirmed |  | 0
System Installed & Tested |  | 0
Backup Systems & Protocol |  | 0
Workstations
Requirements determined |  | 0
System specifications agreed |  | 0
Service Level Agreement finalised |  | 0
Equipment Orders placed |  | 0
Installation dates confirmed |  | 0
System Installed & Tested |  | 0
Training dates confirmed |  | 0
Printers/Scanner/ Fax
Requirements determined |  | 0
System specifications agreed |  | 0
Service Level Agreement finalised |  | 0
Equipment Orders placed |  | 0
Installation dates confirmed |  | 0
System Installed & Tested |  | 0
Training dates confirmed |  | 0
Software Requirements
Requirements determined |  | 0
Orders placed |  | 0
Licencing
Software Licences obtained |  | 0
TV Licence application |  | 0
Internet Service Provider
Determine ISP |  | 0
Service Level Agreement finalised |  | 0
Domain registered |  | 0
e-mail accounts set-up |  | 0
Internet connectivity |  | 0
Telephone System
Confirm Switchboard Specifications |  | 0
Training dates confirmed |  | 0
Arrange Telkom Application |  | 0
Finalise Hotel Phone Number |  | 0
Finalise Hotel Fax Number |  | 0
Arrange Fax to Mail Facility |  | 0
Complete On-Hold Message Recording |  | 0
In-Room Entertainment
Specify requirements |  | 0
Order Decoders |  | 0
Installation & Testing |  | 0
Determine Bouquet |  | 0
Obtain licencing |  | 0
Source Public Area Music |  | 0
Timekeeping System
Requirements determined |  | 0
System specifications agreed |  | 0
Equipment Orders placed |  | 0
Installation dates confirmed |  | 0
System Installed & Tested |  | 0

## LEGAL COMPLIANCE
LEGAL COMPLIANCE | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Business Registration
Obtain business trading number | Completed | 237 | 2018-01-07 | 2018-09-01
Licensing
Trading licence |  | 0
TV Licence |  | 0
Promotion of Access to Information Act
Fire Clearance Certificate obtained |  | 0
Employment Equity
Job Classifications verified |  | 0
Skills Development
Skills Development Facilitator appointed |  | 0
Training Committee established |  | 0
Health and Safety
Health & Safety Representatives appointed |  | 0
First Aiders trained and appointed |  | 0
Health & Safety Committee established |  | 0
First Aid Boxes equipped and available |  | 0

## MARKETING PLAN
MARKETING PLAN | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Hotel Positioning
Develop Hotel USPs per Market Segment | Pending | 237 | 2018-01-07 | 2018-09-01
Complete Competitor Analysis |  | 0
Complete SWOT Analysis |  | 0
Hotel Sales Collateral
Develop facilities guide/presentation folder |  | 0
Develop Pre-Opening Brochure |  | 0
Develop Permanent Brochure |  | 0
Develop ancillary sales collateral/stationery |  | 0
Develop Press Kit |  | 0
Develop Property Maps |  | 0
Photography/Video |  | 0
Coordinate photo shoot for permanent brochure |  | 0
Photography available |  | 0
Marketing Plan
Appoint Marketing Plan Co-Ordinator |  | 0
Appoint Sales Executive |  | 0
Acquisition Plan to be formulated |  | 0
Acquisition Plan to be approved |  | 0
Rates Structure
Complete and Submit Rate Builder |  | 0
Rate Grid to be approved |  | 0
Soft Opening Programme
Determine Target Groups |  | 0
Determine pre-opening programmes |  | 0
Hotel Opening Programme
Determine official opening date |  | 0
Determine Target Groups |  | 0
Determine Programme |  | 0
Hotel Branding
Minimum Branding Requirements ascertained |  | 0
Minimum Branding Requirements ordered |  | 0
Hotel Brochure finalised |  | 0
Hotel Signage finalised |  | 0
Corporate Flags ordered |  | 0
Rates Board ordered |  | 0
Brochure Rack and Brochures ordered |  | 0
Hotel Stationery finalised and ordered |  | 0
Key Cards designed |  | 0
Internal Signage agreed |  | 0
Marketing Material ordered |  | 0
Branding Checklist Completed |  | 0
Hotel Web Page
Hotel.com Web Entry |  | 0
Hotel Fact Sheet submitted |  | 0
Pictures submitted |  | 0

## QUALITY PLAN - F&B
QUALITY PLAN - F&B | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Contract GUEST Valet/ Laundry | Completed | 237 | 2018-01-07 | 2018-09-01
Contract GUEST Transport |  | 0
Develop F&B Outlet Concepts |  | 0
Restaurant Concept |  | 0
Restaurant Theme |  | 0
STAFFING LEVELS |  | 0
Service Levels |  | 0
Menu Planning |  | 0
Menu Tastings |  | 0
Menu Costings |  | 0
Develop Standard Recipes |  | 0
Menu Pricing finalised |  | 0
Menus to Print |  | 0
Table Layouts |  | 0
Centrepieces |  | 0
Linen/ Table Mats |  | 0
Bar Concept
Operating Hours |  | 0
STAFFING Levels |  | 0
Wine List Finalised |  | 0
Wine List Costed |  | 0
Drinks Pricing |  | 0
Service Levels |  | 0
Room Service
Operating Hours |  | 0
STAFFING Levels |  | 0
Service Levels |  | 0
Menu Planning |  | 0
Menu Costings |  | 0
Menu Pricing finalised |  | 0
Menus to Print |  | 0
Equipment specifications |  | 0
Equipment ordered (see Purchasing) |  | 0
Equipment commissioning complete |  | 0
Kitchen
Determine Kitchen smallwares |  | 0
Specify kitchen smallwares |  | 0
Order kitchen smallwares |  | 0
Delivery date confirmed |  | 0
Equipment commissioning complete |  | 0
Purchasing
Linen |  | 0
Specifications confirmed |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
Cutlery |  | 0
Specifications confirmed |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
Crockery |  | 0
Specifications confirmed |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
Glassware |  | 0
Specifications confirmed |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
Equipment |  | 0
Specifications confirmed |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
F&B Inventories |  | 0
Develop Kitchen par stock |  | 0
Develop master beverage/bar par stock and wine list |  | 0
Procure opening F&B inventories |  | 0
Conferencing
Conferencing Layouts |  | 0
Conferencing Packages |  | 0
Specify Conferencing Equipment |  | 0
Order Conferencing Equipment |  | 0
Delivery Dates Confirmed |  | 0
Equipment commissioning complete |  | 0
Technical support available |  | 0
Storage and Control
Arrange suitably secured storage |  | 0
Complete Asset Register |  | 0
Complete Opening Stock Inventories |  | 0
Obtain Quality Operating Standards Manual |  | 0
Issue Minimum Operating Standards to Heads of Departments |  | 0
Customise Minimum GUEST Service Standards |  | 0
Communicate Minimum GUEST Service Standards |  | 0
Schedule Pre-opening Quality Assurance Assessment |  | 0
Obtain required SA Grading |  | 0
Implement "Hot or Not" GUEST Feedback System |  | 0

## QUALITY PLAN - Housekeeping
QUALITY PLAN - Housekeeping | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Obtain Quality Operating Standards Manual | In Progress | 237 | 2018-01-07 | 2018-09-01
Issue Minimum Operating Standards to Heads of Departments |  | 0
Customise Minimum GUEST Service Standards |  | 0
Communicate Minimum GUEST Service Standards |  | 0
Schedule Pre-opening Quality Assurance Assessment |  | 0
Obtain required Standard Assessment Grading |  | 0
Implement GUEST Feedback System |  | 0
HOUSEKEEPING
Equipment |  | 0
Requirements Specified |  | 0
Housekeeping Trolleys |  | 0
Vacuum Cleaners |  | 0
Cleaning Smalls |  | 0
Quantities and Specifications established |  | 0
Delivery Dates Confirmed |  | 0
Asset Register opened |  | 0
Linen
Quanities Specified |  | 0
Par Stock Established |  | 0
Quality Specifications Set |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
Secure Storage |  | 0
Opening Inventory Taken |  | 0
GUEST Supplies
GUEST Bathroom Amenities |  | 0
GUEST Stationery |  | 0
GUEST Beverage Supplies |  | 0
Quanities Specified |  | 0
Par Stock Established |  | 0
Quality Specifications Set |  | 0
Orders Placed |  | 0
Delivery Dates Confirmed |  | 0
Secure Storage |  | 0
Opening Inventory Taken |  | 0
Minimum Branding
Checklist Completed |  | 0
Outsourcing |  | 0
Housekeeping Contract Cleaning |  | 0
Service Level Agreement finalised |  | 0
Laundry |  | 0
Service Level Agreement finalised |  | 0
Public Area Contract Cleaning |  | 0
Service Level Agreement finalised |  | 0
All Contractors to undergo Induction Training |  | 0

## RISK MANAGEMENT
RISK MANAGEMENT | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Obtain Risk Management Manual | Completed | 25 | 2018-01-07 | 2018-02-01
Complete Risk Management Plan |  | 0
Insurance
Determine Insurance Needs |  | 0
Confirm Insurance Providers |  | 0
Ensure Insurance is activated |  | 0
Arrange Risk Audit post opening |  | 0
Emergency Planning
Draft Emergency Procedures |  | 0
Draft Evacuation Procedures |  | 0
Obtain Emergency Services Contact Numbers |  | 0
Appoint Fire Station Officers |  | 0
Train STAFF in Emergency Procedures |  | 0
Hold Fire & Evacuation Drill |  | 0
Health & Safety
Order First Aid Boxes |  | 0
Order Emergency Equipment |  | 0
Megaphones |  | 0
Hard Helmets |  | 0
Vests |  | 0
2-way radios |  | 0
Torches |  | 0
Verify proper operation of all Life Safety equipment/systems |  | 0
GUEST Security
Check CCTV installation & monitoring |  | 0
Key Register & Monitoring System in place |  | 0
Computer Security |  | 0
Backup Systems & Procedures in place |  | 0
Electronic Communication Policy in Place |  | 0

## STAFFING
STAFFING | Status | Duration ( Days ) | Start | Due / Finish | Task Assigned / Owned By | Remarks
Finalise STAFFING Numbers | Pending | 237 | 2018-01-07 | 2018-09-01
Finalise Salary & Benefits Budget |  | 0
Obtain HR Operating Standards Manual |  | 0
Establish Conditions of Employment |  | 0
Draw up Contracts of Employment |  | 0
Confirm Employment Policies |  | 0
Establish Hotel Rules |  | 0
Obtain HR Forms |  | 0
Establish Performance Expectations
Issue Job Descriptions |  | 0
Issue GUEST Service Standards |  | 0
Arrange for Probationary Performance Reviews |  | 0
Determine Outsourcing Requirements
Housekeeping |  | 0
Service Level Agreement finalised |  | 0
Laundry |  | 0
Service Level Agreement finalised |  | 0
Contract Cleaning |  | 0
Service Level Agreement finalised |  | 0
Maintenance |  | 0
Service Level Agreement finalised |  | 0
Security |  | 0
Service Level Agreement finalised |  | 0
STAFF Transport |  | 0
Service Level Agreement finalised |  | 0
Customise Position Specifications |  | 0
Develop Hiring Schedule |  | 0
Develop Training Schedules |  | 0
Confirm Training Dates & Providers |  | 0
Hire Senior Management Team
Operation Manager |  | 0
Asst.Operation Manager |  | 0
Hire Department Heads
Accounting Spv |  | 0
FO Spv |  | 0
HK Spv |  | 0
Sales Executive |  | 0
Eng Spv |  | 0
Hire Junior Management
Hire Service and Support STAFF |  | 0
Schedule Training
Induction Training |  | 0
Skills Training |  | 0
Systems Training (PMS & POS) |  | 0
Emergency Procedures |  | 0